DISTRIBUTED ASSESSMENT

What remains before production rollout

Branch: codex/distributed-lab-assessment  |  Current commit: 304f107  |  Audience: faculty, IT, and release owner

Bottom line The product implementation is complete for the agreed design: one coordinator plus separately installed Windows clients, local answering and timers, same questions in a per-student order, same-computer resume, and sealed result submission. The remaining work is release and deployment readiness, not a redesign of the assessment workflow.

# Current status

The source branch contains the distributed coordinator/client implementation, protected client service boundary, durable local outbox, outage recovery, faculty controls, compatibility migration, separate Windows packaging, and the configurable saved coordinator URL workflow.

Verification already recorded: the canonical Node-enabled suite passed 462/462; focused recovery/migration/installer/checkpoint tests passed 22/22; the latest client-store correction passed 59/59 focused tests; 30-client, 100-client, and 100-client outage/restart gates passed their correctness and submission thresholds. The outage run has one explicitly accepted local-answer p99 miss (109.184 ms versus the unchanged 100 ms target). The 462-test and load-gate runs predate commit 304f107, so the latest commit still needs a final independent review and, if required by the release owner, a final evidence rerun.

The current release folder contains separate coordinator and client executables/installers plus SHA-256 hashes. Those artifacts are verification builds only until the institution supplies its production Authenticode identity and timestamp service.

# Remaining work: required gates

| Priority / status | Remaining work | Why it is required | Completion evidence |
| --- | --- | --- | --- |
| BLOCKING — release | Supply the institution-controlled signing inputs: PFX, protected password, exact publisher subject, and HTTPS timestamp URL. Run the fail-closed production build and regenerate hashes. | The current test-signed binaries must not be distributed as production installers. | Production build completes; Authenticode publisher, timestamp, inner/installer signatures, recursive payload scan, smoke, and hashes all pass. |
| BLOCKING — assurance | Run the final scoped independent review against commit 304f107, including the atomic legacy-state migration and transient-anchor recovery correction. | The latest correction was focused-tested but has not yet received a fresh independent sign-off in the recorded review ledger. | Reviewer records no Critical or Important findings for the final commit. |
| BLOCKING — physical acceptance | On disposable authorized Windows machines, install coordinator and client packages, verify LocalSystem service ownership, protected ACLs, machine-root CA, private firewall rule, loopback-only client UI, enrollment, one assessment, and coordinator outage/restart. | Automated isolated tests cannot prove Windows service, ACL, certificate-store, firewall, or installer behavior on intended hardware. | Signed acceptance checklist and logs from one coordinator plus representative lab clients. |
| CONDITIONAL — data | If an existing pre-2.0 Aptitude Lab database must be retained, take a complete backup, run the compatibility migration dry-run, review counts/integrity, then perform the confirmed additive migration. | Skipping the controlled migration risks losing historical students, attempts, responses, scores, or keys. | Dry-run report approved; live migration backup and post-migration integrity/row-count checks match. |

# Remaining work: deployment and operations

| Step | Action | Owner | Done when |
| --- | --- | --- | --- |
| 1 | Choose a stable DNS hostname and approved private HTTPS port; obtain the matching certificate and private-profile firewall approval. | IT / security | Every lab computer resolves the name and the coordinator is reachable only on the approved private profile. |
| 2 | Install the signed KSAT Coordinator package, initialize it, and back up the complete ProgramData tree including database, keys, releases, certificates, and configuration. | Faculty IT | A restore-ready backup exists and the public CA/metadata export is verified. |
| 3 | Install the signed KSAT Client package on each lab computer, initially save the coordinator URL, and distribute only the public CA/metadata files. | Lab IT | Each client opens only 127.0.0.1:8010 and ordinary lab users cannot write protected state. |
| 4 | Rotate the one-time enrollment code, enroll the named lab computers, confirm active status, then rotate the code again. | Faculty | The Devices page lists the intended machines and the enrollment code is no longer valid. |
| 5 | Import/validate the question bank, create the assessment, prefetch the encrypted pack, launch once, and monitor queue/started/submitted counts. | Faculty | A supervised pilot completes with local answering, same-computer resume, timer behavior, and authoritative score receipt. |
| 6 | Exercise backup restore and coordinator outage recovery before the first high-stakes assessment. | Faculty IT | A disposable restore and one stop/restart rehearsal complete without data loss or manual SQLite edits. |

# Optional follow-up (not required to start a controlled pilot)

| Status | Item | Decision |
| --- | --- | --- |
| OPTIONAL | Optimize the outage-gate local-answer p99 from 109.184 ms to below 100 ms. | The miss is narrow, isolated to outage mode, and was explicitly accepted. Defer unless the institution requires the strict target. |
| OPTIONAL | Repeat redundant load gates or a full release build after every documentation-only change. | Only rerun when release evidence must be tied to a newly rebuilt artifact or a code change affects the measured path. |
| OPTIONAL | Restructure the multi-commit integration history into a clean branch. | Explicitly deferred by the reduced-scope instruction; do not rewrite history as part of rollout. |
| OPTIONAL | Expand physical acceptance from the representative pilot to the complete lab fleet. | Do this as a normal staged rollout after the pilot and restore rehearsal pass. |

# Recommended safe-and-fast order

1. Obtain production signing inputs and run the fail-closed production build.  2. Obtain final independent review sign-off on commit 304f107.  3. Perform the authorized disposable-machine acceptance test.  4. If needed, migrate legacy data from a protected copy.  5. Install and enroll a small pilot, run one supervised assessment, and rehearse restore/outage recovery.  6. Roll out to the remaining lab computers.

Stop condition Do not distribute the current verification binaries, copy private coordinator secrets, bypass TLS validation, or edit client SQLite files manually. If any physical acceptance or migration check fails, preserve the complete data tree and use the documented rollback path.

# Reference files

Operational procedures: docs/distributed-assessment-operations.md. Windows build and signing procedure: WINDOWS_EXE_BUILD.md. Product overview and installation notes: README.md. Load-gate reports: load-report-30.json, load-report-100.json, and load-report-100-outage.json in the distributed worktree.